## Issue Tracker
Preva Kitchen — SEO Audit Status
Checked against live prevakitchen.com and the codebase on 15 Oct 2026 · 47 issues · Fixed: 26 · Fixed (goes live on next deploy): 6 · Partially fixed: 5 · Not Started: 10
ID | Phase | Priority | Category | Issue | Affected URL(s) | What was fixed | How to check (manually) | Status
SEO-01 | Phase 1 – Critical | P0 | Technical – Metadata | Careers page canonical & OG images point to localhost | /careers | Canonical and OG/Twitter images now use https://prevakitchen.com. | Open view-source:https://prevakitchen.com/careers → Ctrl+F "localhost" → 0 results. Canonical = https://prevakitchen.com/careers. | Fixed
SEO-02 | Phase 1 – Critical | P0 | Technical – Metadata | Meta description / OG / canonical missing from <head> | /, /about, /contact, /blog, /reservations | Metadata is rendered inside <head> on every page (htmlLimitedBots). | View-source of each page → title, meta description, canonical and og: tags appear before </head>. | Fixed
SEO-03 | Phase 1 – Critical | P0 | Content – Duplicate URLs | Same dish listed twice with different URLs & prices | /menu, /menu/preva-* | Duplicates removed from the menu; old slugs 301/308 to the surviving dish in one hop; sitemap has only canonical slugs. | Open /menu → Lamb Chops, Steak Bites, Lobster, Mac & Cheese appear once. Open /menu/preva-lamb-chops → lands on /menu/lamb-chops. | Fixed
SEO-04 | Phase 1 – Critical | P0 | Content – Data Consistency | Prices differ between home, menu and dish pages | /, /menu, /menu/[dish] | Home "Preva Favorites" and category cards are built from the live menu data (one source of truth). | Pick 3 dishes; compare price on home, /menu and the dish page — identical. | Fixed
SEO-05 | Phase 1 – Critical | P0 | Local SEO – NAP | Email, phone link and hours inconsistent | All pages | Every page uses info@prevakitchen.com and tel:+13132863586. | Ctrl+F on any page footer: only info@prevakitchen.com; phone link is tel:+13132863586. Check hours text by eye. | Fixed
SEO-06 | Phase 1 – Critical | P0 | Technical – Internal Links | Broken / wrong internal links and anchors | Header, sticky bar, /contact | Header & mobile menu "Reservations" now link to /reservations (was /#prv-reservations). Other links were already fixed live. | After deploy: click Reservations in the header on any page → opens /reservations. | Fixed (goes live on next deploy)
SEO-07 | Phase 1 – Critical | P0 | Technical – Rendering | Blog loads client-side – no crawlable content | /blog | Blog list is server-rendered with links to each post. | View-source of /blog → post titles and <a href="/blog/..."> links are present. | Fixed
SEO-08 | Phase 2 – High | P1 | Structured Data | Restaurant (LocalBusiness) JSON-LD | / (global) | Restaurant schema with address, geo, hours, menu and reservation. | search.google.com/test/rich-results → test https://prevakitchen.com → no errors. | Fixed
SEO-09 | Phase 2 – High | P1 | Structured Data | Menu / MenuItem / Offer + Breadcrumb schema | /menu, /menu/[dish] | Dish pages have MenuItem, Offer, Product, BreadcrumbList and FAQPage. | Rich Results Test on /menu/lamb-chops → Breadcrumb + FAQ detected. | Fixed
SEO-10 | Phase 2 – High | P1 | Structured Data | JobPosting schema + missing salary | /careers/*-redford | JobPosting schema live. "Pay range pending confirmation" is now hidden; baseSalary only added when a real range exists. | After deploy: open a job page → no "pending" pay line. Rich Results Test → Job posting eligible. | Partially fixed
SEO-11 | Phase 2 – High | P1 | On-Page – Headings | Home H1 has no keyword | / | H1 = "Preva Kitchen – Restaurant in Redford Township, MI"; title has brand + location. | Home page → right-click heading → Inspect → only one <h1> with brand + location. | Fixed
SEO-12 | Phase 2 – High | P1 | On-Page – Headings | Weak H1s + broken heading order on /menu | /menu, /contact, /blog, /careers | New keyword H1s; menu categories are H2, dishes H3. | Use the HeadingsMap browser extension → one H1 and H2→H3 order on each page. | Fixed
SEO-13 | Phase 2 – High | P1 | Content – Accuracy | Home category cards show fake counts | / | Cards built from real menu categories; each links to its category page. | Home → "Our Delicious Categories" → each card opens /menu/category/<name>. | Fixed
SEO-14 | Phase 2 – High | P1 | Site Architecture | No category landing pages | /menu/category/* | 10 category pages (wings, burger, tacos, pasta…) live and in the sitemap. | Open /menu/category/wings → 200 with its own title and H1. | Fixed
SEO-15 | Phase 2 – High | P1 | URL Structure | Wing flavour URLs too generic (/menu/buffalo…) | /menu/buffalo, /bbq, /jerk… |  |  | Not Started
SEO-16 | Phase 2 – High | P1 | Content – Thin / Templated | Dish FAQ template grammar + wrong related items | /menu/[dish] | FAQ/About copy fixed ("What are the Buffalo Wings…?", "What are Preva Lamb Chops?"); same text in FAQ schema. Related dishes show same category first. | After deploy: open /menu/buffalo and /menu/lamb-chops → read the FAQ questions; "More …" section shows same-category dishes first. | Fixed (goes live on next deploy)
SEO-17 | Phase 2 – High | P1 | On-Page – Meta | Dish meta descriptions cut mid-word | /menu/[dish] | Descriptions ≤155 chars and always end with "Order pickup or delivery from Preva Kitchen in Redford Township, MI." | After deploy: view-source /menu/lamb-chops → meta description ends with a full sentence. | Fixed (goes live on next deploy)
SEO-18 | Phase 2 – High | P1 | Images | Wrong / generic dish image & OG image | /menu/lamb-chops | Lamb Chops uses its real photo as product and OG image. | View-source /menu/lamb-chops → og:image = prevaLamb-600x600.webp. | Fixed
SEO-19 | Phase 2 – High | P1 | Images | Stock (Unsplash) photos used as real food photos | /, /menu |  |  | Not Started
SEO-20 | Phase 2 – High | P1 | Content – Placeholders | Internal / placeholder notes visible | /about, /careers | /about has no placeholder text (live). Careers "pay pending" line hidden (deploy pending). | After deploy: Ctrl+F "pending" / "coming soon" on /about and a job page → 0 results. | Fixed (goes live on next deploy)
SEO-21 | Phase 2 – High | P1 | Performance – CWV | Home hero autoplays a heavy 1080p MP4 | / | Video re-encoded 49 MB → 12.9 MB at the same 1080p quality; loads only after the page; WebP poster; phones get the poster. Local Lighthouse desktop 67 → 82, LCP 5.9 s → 2.2 s. | After deploy: PageSpeed Insights on https://prevakitchen.com (desktop & mobile); DevTools → Network → video starts after "load". | Fixed (goes live on next deploy)
SEO-22 | Phase 2 – High | P1 | Technical – Crawl | XML sitemap & robots.txt | /sitemap.xml, /robots.txt | Sitemap has canonical URLs only; robots blocks admin/api/checkout and points to the sitemap. | Open /sitemap.xml and /robots.txt in the browser. | Fixed
SEO-23 | Phase 2 – High | P1 | Tracking & Tools | GSC, Bing, GA4 setup; GTM missing on some pages | /blog, /contact, /careers | GTM (GTM-TBSJ2TTS) now on every page. | Tag Assistant / view-source → GTM-TBSJ2TTS on /blog, /contact, /careers. | Partially fixed
SEO-24 | Phase 2 – High | P1 | Technical – Layout | Two different header/footer layouts | All pages | One shared header and footer across the site. | Compare footer on /, /blog, /contact, /careers → identical. | Fixed
SEO-25 | Phase 3 – Medium | P2 | Images | Heavy JPG/PNG heroes, no responsive sizes | /, gallery | Home hero, mobile hero, gallery and booking images switched to WebP (e.g. 1.6 MB PNG → 104 KB). | After deploy: PageSpeed → "Improve image delivery" savings much smaller. | Partially fixed
SEO-26 | Phase 3 – Medium | P2 | Performance – 3rd party | Google Maps iframe on every page | All pages | No Maps iframe in the footer. | DevTools → Network on home → no maps.googleapis.com requests. | Fixed
SEO-27 | Phase 3 – Medium | P2 | Accessibility / On-Page | Menu cards: duplicate links, stuffed link text | /menu | No button nested inside links; link text is the dish name. | Lighthouse → Accessibility on /menu → no nested-interactive warning. | Fixed
SEO-28 | Phase 3 – Medium | P2 | Accessibility | Icon links without accessible names | Header | Phone icon has aria-label "Call Preva Kitchen at (313) 286-3586". | Lighthouse → Accessibility → no "links do not have a discernible name". | Fixed
SEO-29 | Phase 3 – Medium | P2 | Images – Alt text | Poor / awkward alt texts | /, /menu | Reservation image alt rewritten ("Guests enjoying dinner together…"). | Inspect the reservation image on home → new alt text. | Fixed
SEO-30 | Phase 3 – Medium | P2 | UX / Conversion | Two different reservation forms | /, /reservations | Home and /reservations use the same booking form; header link goes to /reservations (deploy pending). | Fill the form on home and on /reservations → both appear in Admin → Leads. | Fixed (goes live on next deploy)
SEO-31 | Phase 3 – Medium | P2 | UX / Content | "On today's menu" always shown | /menu/[dish] | Static availability text removed. | Open any dish page → no "On today's menu" line. | Fixed
SEO-32 | Phase 3 – Medium | P2 | Local SEO – E-E-A-T | No reviews / testimonials on site | /, /about |  |  | Not Started
SEO-33 | Phase 3 – Medium | P2 | Local SEO | Google Business Profile alignment | Off-site |  |  | Not Started
SEO-34 | Phase 3 – Medium | P2 | Technical – Status codes | 404 handling for unknown slugs | /menu/x, /careers/x | Unknown dish/job slugs return HTTP 404. | Open https://prevakitchen.com/menu/test-123 → 404 page. | Fixed
SEO-35 | Phase 3 – Medium | P2 | Technical – Redirects | Single-hop redirects http→https, www→non-www | Site-wide | https://www → non-www is one hop; http://www still takes two hops. | curl -I http://www.prevakitchen.com → should go straight to https://prevakitchen.com/. | Partially fixed
SEO-36 | Phase 3 – Medium | P2 | Technical – Cloudflare | Make sure Cloudflare doesn't block search/AI bots | Site-wide |  |  | Not Started
SEO-37 | Phase 3 – Medium | P2 | Content – Catering | Catering links to redirecting dish URLs | /catering | All catering dish links use canonical slugs. | Hover the catering dish links → /menu/lamb-chops etc. (no preva- slugs). | Fixed
SEO-38 | Phase 3 – Medium | P2 | Content – Brand | Brand name & UK spelling consistency | Site-wide |  |  | Not Started
SEO-39 | Phase 3 – Medium | P2 | Footer / Trust | Privacy & Terms links missing in footers | All pages | Every footer links /privacy-policy and /terms. | Scroll to the footer on any page → Privacy Policy & Terms links. | Fixed
SEO-40 | Phase 4 – Low | P3 | On-Page – Meta | Remove meta keywords tag | All pages | No meta keywords on any page. | View-source → Ctrl+F name="keywords" → 0 results. | Fixed
SEO-41 | Phase 4 – Low | P3 | URL / Assets | Clean up asset paths & file names | /asset/prevaclub/wp-content/… |  |  | Not Started
SEO-42 | Phase 4 – Low | P3 | Local SEO – Content | Service-area content for nearby cities | New pages |  |  | Not Started
SEO-43 | Phase 4 – Low | P3 | Content – Blog | Blog content plan | /blog | Blog has published posts. | Open /blog → posts listed. | Partially fixed
SEO-44 | Phase 4 – Low | P3 | Content – Menu | Thin categories (1 dish each) | /menu |  |  | Not Started
SEO-45 | Phase 4 – Low | P3 | Structured Data | Order & reservation actions in schema | / (Restaurant JSON-LD) | OrderAction and ReserveAction present in the Restaurant schema. | View-source home → Ctrl+F "OrderAction" and "ReserveAction". | Fixed
SEO-46 | Phase 4 – Low | P3 | Technical – PWA basics | Favicon, apple-touch-icon, manifest, theme-color | Site-wide | All four present. | View-source → icon, apple-touch-icon, manifest and theme-color tags. | Fixed
SEO-47 | Phase 4 – Low | P3 | Monitoring | Monthly SEO health check | Ongoing |  |  | Not Started

## Summary
Status summary
How many audit issues are in each state
Status | Issues | Phase | Fixed | Fixed – next deploy | Partially fixed | Not Started
Fixed | 26 | Phase 1 – Critical | 6 | 1 | 0 | 0
Fixed (goes live on next deploy) | 6 | Phase 2 – High | 9 | 4 | 2 | 2
Partially fixed | 5 | Phase 3 – Medium | 8 | 1 | 2 | 4
Not Started | 10 | Phase 4 – Low | 3 | 0 | 1 | 4
Total | 47
Legend
Fixed | Fixed and checked on prevakitchen.com
Fixed (goes live on next deploy) | Fixed in the code, shows on the live site after the next deploy
Partially fixed | Part of it is fixed
Not Started | Not done yet

## Other Work Done
Other work done (outside the audit list)
Website forms, admin Leads page and speed work
Item | What was done | Status | How to verify
Leads page in admin | Admin → Inbox → Leads: every website form (contact, reservations, events, careers with CV preview/download, newsletter, VIP, guest list) in one list, with filters, preview drawer, status, page URL and a formatted Excel download. | Fixed (goes live on next deploy) | Log in to admin → Inbox → Leads; submit a test form and see it appear.
Form submissions always saved | Forms that were emailed but not saved (21–30 guests, closed job roles, Word CV type, 5+ forms from one IP, CMS form block) now always reach the admin too. | Fixed (goes live on next deploy) | Submit a reservation for 25 guests → it appears in Leads and in email.
Home page speed | Hero video 49 MB → 12.9 MB (same quality), images to WebP, video and slides load after the page. | Fixed (goes live on next deploy) | PageSpeed Insights after deploy.